## Defect Tracker
Sl No | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status | Remarks
1 | 20-11-2025 | Database seeding fails due to foreign key constraint on Airport codes. | Sprint 1 | Backend Team | Functional | Re-ordered seeding sequence: Airports first, then Flights. | 21-11-2025 | Closed | Schema verified.
2 | 24-11-2025 | Search results showing flights with departure dates in the past. | Sprint 1 | Backend Team | Logic | Added validation filter departure_time >= now() in SQL query. | 25-11-2025 | Closed | Filter working.
3 | 29-11-2025 | User registration allows duplicate email addresses. | Sprint 2 | Backend Team | Security/DB | Added UNIQUE constraint to email column and handled IntegrityError. | 30-11-2025 | Closed | Validated with Postman.
4 | 2025-02-12 | Dynamic price shifts to zero when seat availability is 100%. | Sprint 2 | Backend Team | Algorithmic | Added a Base_Fare constant to the pricing engine formula. | 2025-03-12 | Closed | Logic stable.
5 | 2025-07-12 | Celery workers not picking up demand simulation tasks. | Sprint 3 | DevOps | Infrastructure | Fixed Redis URL in environment variables and restarted worker. | 2025-08-12 | Closed | Task queue active.
6 | 2025-10-12 | Double booking occurred during high-speed parallel click test. | Sprint 3 | Backend Team | Concurrency | Implemented with_for_update() to lock flight rows during booking. | 2025-11-12 | Closed | Critical fix.
7 | 16-12-2025 | Passenger form crashes when entering special characters in name. | Sprint 4 | Frontend Team | UI/Validation | Added RegEx validation to input fields and sanitized backend inputs. | 17-12-2025 | Closed | Sanitized.
8 | 23-12-2025 | PNR generation occasionally returns 5 characters instead of 6. | Sprint 5 | Backend Team | Logic | Updated string generator to ensure fixed-width output. | 24-12-2025 | Closed | Verified PNR length.
9 | 30-12-2025 | PDF Ticket QR code not scanning on mobile devices. | Sprint 6 | Backend Team | Functional | Increased QR code error correction level and image resolution. | 31-12-2025 | Closed | Scans correctly.
10 | 2026-03-01 | Admin Dashboard showing "NaN" for total revenue when no bookings exist. | Sprint 6 | Frontend Team | UI | Added null-coalesce operator to display "0" instead of NaN. | 2026-04-01 | Closed | UI looks clean.